## Slide 1
APPENDIX
What the appendix contains
1
A1
Detailed close calendar
Day-by-day view of the current close for 14 entities
p. 36
A2
Entity readiness assessment
Scores for data, process and system readiness
p. 37
A3
Control framework
Key controls mapped to the target operating model
p. 39
A4
Tooling options
Comparison of three automation platforms
p. 41
A5
Assumptions and fee detail
Rate card basis, phase fees and exclusions
p. 42
A6
Selected client references
Four comparable healthcare finance programs
p. 44
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 2
2
A
SUPPORTING DETAIL
Appendix
Six reference items, A1 to A6, on pages 36 to 44.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 3
3
A
SUPPORTING DETAIL
Appendix
Six reference items, A1 to A6, on pages 36 to 44.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 4
4
APPENDIX
Reference material
Detail for readers who want to check the numbers and the sources behind the proposal.
A1
Detailed close calendar
Day-by-day view of the current close for 14 entities
A2
Entity readiness assessment
Scores for data, process and system readiness
A3
Control framework
Key controls mapped to the target operating model
A4
Tooling options
Comparison of three automation platforms
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 5
EPIC BREAKDOWN
Self-scheduling splits into four features and nine stories
Source: Northfield digital front door backlog, Oct 2026. Sample figures for layout only.
5
EPIC E-101
Self-scheduling
Patients book, move and cancel visits in the app without a call.
33
points, four features
31
acceptance criteria
USER STORY | AC | POINTS | STATUS
As a patient, I want to search open slots by provider | 4 | 3 | Done
As a patient, I want to filter by location and time | 3 | 3 | Done
As a patient, I want to pick a visit type and book | 5 | 8 | In progress
As a patient, I want a booking confirmation | 3 | 2 | In progress
As a patient, I want to reschedule from the app | 4 | 5 | In progress
As a patient, I want to cancel and free the slot | 3 | 3 | Not started
As a patient, I want a text reminder with a link | 4 | 5 | Not started
As a patient, I want to add the visit to my calendar | 2 | 2 | Not started
As a patient, I want a day-before prep note | 3 | 2 | Blocked
FIND
BOOK
CHANGE
NOTIFY
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 6
DIGITAL FRONT DOOR BACKLOG
Eight epics carry the front door; access and estimates lead
Source: Northfield digital front door backlog, Oct 2026. Sample figures for layout only.
6
EPIC | OUTCOME | PRIORITY | SIZE | STATUS | RELEASE
Self-scheduling | Book and move visits without a call |  | XL | In progress | 4.1 · Nov
Waitlist and cancellations | Refill released slots within hours |  | L | In progress | 4.2 · Jan
Digital intake | Arrive with forms and consents done |  | L | In progress | 4.1 · Nov
Cost estimates | Show the patient price before the visit |  | XL | Not started | 4.2 · Jan
Bill pay | Pay a statement in two taps |  | M | Done | 4.0 · Oct
Payment plans | Set up a plan without calling billing |  | L | Not started | 4.3 · Mar
Secure messaging | Reach the care team in one thread |  | L | Blocked | 4.2 · Jan
Proxy access | Let caregivers act for family members |  | M | Not started | 4.3 · Mar
P1
P2
P1
P1
P2
P3
P2
P4
ACCESS
MONEY
ENGAGE
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 7
BACKLOG HEALTH
The next two sprints are ready; the tail is aging
Source: Northfield digital front door backlog, Oct 2026. Sample figures for layout only.
7
42
ready items, of 118 open
88%
refined for the next two sprints
47
days average backlog age
AT RISK
6
blocked items
AT RISK
28%
of open items are bugs, 72% features
Open items by age
ITEMS
Chart: 
| 0 TO 30 DAYS | 31 TO 60 | 61 TO 90 | OVER 90
Items | 52 | 34 | 19 | 13
01
Refinement is on track
Next two sprints hold 88% refined stories.
02
Messaging is stuck
Five of six blocked items wait on the vendor API.
03
Old items need a verdict
13 items over 90 days: close, split or schedule.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 8
WORKING AGREEMENTS
A story must be ready to start and done to count
Source: Northfield digital front door backlog, Oct 2026. Sample figures for layout only.
8
DEFINITION OF READY
A story enters a sprint when
Story states who, what and why
Acceptance criteria are testable
Designs are linked and reviewed
Dependencies are named and clear
Estimated by the team at 8 points or less
Product owner has ranked it
Fits in one sprint
DEFINITION OF DONE
A story is done when
Code reviewed and merged
Unit and UI tests pass
Accessibility check passed
Analytics events verified
Release notes drafted
Product owner accepted it
Support team briefed
The product owner owns ready, the delivery team owns done, and both are reviewed in the quarterly retro.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 9
RELEASE PLAN
Three releases take the front door through March
Source: Northfield digital front door backlog, Oct 2026. Sample figures for layout only.
OVERVIEW
PRIORITIZE
PLAN
HEALTH
9
RELEASE 4.1 · NOV 2026
01
Book and arrive ready
Self-scheduling · 33 pts
Digital intake · 20 pts
OUTCOME
Patients book, move and arrive with forms done.
RELEASE 4.2 · JAN 2027
02
Know the price first
Cost estimates · 34 pts
Waitlist offers · 18 pts
Messaging · 8 pts
OUTCOME
Patients see the price before they commit.
RELEASE 4.3 · MAR 2027
03
Pay and share care
Payment plans · 21 pts
Proxy access · 13 pts
Hardening · 14 pts
OUTCOME
Patients settle bills and share care with family.
53 of 60
points planned against capacity
60 of 62
points planned against capacity
48 of 60
points planned against capacity
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 10
RANKED BACKLOG
Twelve ranked items; the top five fill two sprints
10
Value patient time saved and calls avoided.
Urgency payer and vendor dates that cannot move.
Effort team sizing, in S to XL tags.
Risk unblock the messaging vendor first.
CUT LINE
Top 5
fit 48 points, two sprints at capacity.
# | BACKLOG ITEM | EPIC | PRIORITY | SIZE | SPRINT
1 | Saved cards for bill pay | Bill pay |  | S | S25
2 | Reschedule from reminder | Self-scheduling |  | M | S25
3 | Open-slot filters | Self-scheduling |  | M | S26
4 | Estimate at booking | Cost estimates |  | XL | S26
5 | Intake pre-fill | Digital intake |  | L | S26
6 | Waitlist offers | Waitlist |  | L | S27
7 | Message threads | Messaging |  | L | S27
8 | Payment plan setup | Payment plans |  | L | S27
9 | Proxy invite reminders | Proxy access |  | S | Later
10 | Message attachments | Messaging |  | M | Later
11 | Family calendar view | Proxy access |  | M | Later
12 | Wayfinding maps | Wayfinding |  | XL | Later
P1
P1
P2
P2
P2
P2
P2
P3
P3
P3
P4
P4
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 11
SPRINT PLAN
Sprints 24 to 27 commit to 24 points each
11
Sprint 24
OCT 12 TO 23 · CAPACITY 28
Saved cards · 4
Reschedule link · 6
Cancel, free slot · 4
Open-slot filters · 6
Confirmation · 4
Sprint 25
OCT 26 TO NOV 6 · CAPACITY 28
Estimate API · 8
Intake pre-fill · 8
Calendar add · 2
Waitlist offers · 6
Sprint 26
NOV 9 TO 20 · CAPACITY 28
Estimate screen · 8
Message threads · 6
Prep note · 4
Bug burn-down · 6
Sprint 27
NOV 30 TO DEC 11 · CAPACITY 28
Payment plan setup · 8
Proxy invites · 4
Attachments · 4
Hardening · 6
COMMITMENT 24 PTS
Carryover from Sprint 23
Planned story, points shown after the name
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 12
STORY NFHS-214
Reschedule from a text reminder in under a minute
Source: Northfield digital front door backlog, Oct 2026. Sample figures for layout only.
12
USER STORY
As a patient, I want to move a visit from the reminder text, so that I keep my care without calling.
ACCEPTANCE CRITERIA
GIVEN | WHEN | THEN
A reminder text 48 hours out | I tap the link and sign in | My visit opens with a Reschedule action
Open slots with the same provider | I choose a new slot | The old slot is freed and I get a confirmation
No open slots in 14 days | I tap Reschedule | I am offered the waitlist or a call-back
Designs: Figma link placeholder, reschedule flow
5 pts
estimate, planned for Sprint 25
DONE | DEFINITION OF DONE
 | Code reviewed and merged
 | Unit and UI tests pass
 | Accessibility check passed
 | Product owner accepted
DEPENDS ON
NFHS-198 slot search API
Text reminder deep links
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 13
PRIORITIZATION
Three quick wins come first; wayfinding waits
Source: Northfield digital front door backlog, Oct 2026. Sample figures for layout only.
13
Value and effort
QUICK WINS
DO FIRST
BIG BETS
FILL-INS
MONEY PITS
AVOID
LOW
HIGH
EFFORT →
HIGH
LOW
VALUE →
1
2
3
4
5
6
7
8
RANKED BY VALUE OVER EFFORT
1.
Reschedule from reminder
2.
Open-slot filters
3.
Saved cards for bill pay
4.
Estimate at booking
5.
Intake pre-fill
6.
Proxy invite reminders
7.
Family calendar view
8.
Wayfinding maps
READING THE 2X2
01
Quick wins
Items 1 to 3 go into the next sprint.
02
Big bets
Items 4 and 5 are sliced before commitment.
03
Hold
Items 6 to 8 wait for capacity.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 14
PRIORITIZATION
Weighted scoring puts bill pay and reschedule at the top
Source: Northfield digital front door backlog, Oct 2026. Sample figures for layout only.
14
BACKLOG ITEM | VALUE | TIME CRITICALITY | RISK REDUCTION | JOB SIZE | WSJF SCORE | RANK | TIER
Saved cards for bill pay | 5 | 5 | 3 | 2 | 6.5 | 1 | 
Reschedule from reminder | 8 | 8 | 3 | 3 | 6.3 | 2 | 
Open-slot filters | 5 | 3 | 2 | 3 | 3.3 | 3 | 
Estimate at booking | 13 | 13 | 8 | 13 | 2.6 | 4 | 
Intake pre-fill | 8 | 5 | 5 | 8 | 2.2 | 5 | 
Proxy invite reminders | 3 | 2 | 3 | 5 | 1.6 | 6 | 
Message attachments | 3 | 2 | 2 | 5 | 1.4 | 7 | 
Wayfinding maps | 2 | 1 | 1 | 8 | 0.5 | 8 | 
P1
P1
P2
P2
P2
P3
P3
P4
WSJF = (value + time criticality + risk reduction) divided by job size, each on a 1, 2, 3, 5, 8, 13 scale.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 15
THANK YOU · NORTHFIELD HEALTH SYSTEM
westmonroe.com
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 16
NEXT STEPS
Three steps take us from decision to a January kick-off
16
01
Confirm scope
Agree wave 1 entities and the executive sponsor by 31 October.
02
Mobilize the team
Name your process owners and set the kick-off agenda in November.
03
Kick off wave 1
Start discovery with the five highest-delay entities in January.
DECISION REQUESTED
Approve the wave 1 scope and name an executive sponsor by 31 October.
YOUR CONTACTS
Engagement partner
name@westmonroe.com
Delivery director
name@westmonroe.com
Finance transformation lead
name@westmonroe.com
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 17
NEXT STEP
Kick off wave 1 in January
Engagement partner
name@westmonroe.com
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 18
Questions ?
Ask now, or reach us at any time. We will answer within one working day.
PROPOSAL CONTACTS
Engagement partner
Delivery director
name@westmonroe.com
name@westmonroe.com
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 19
Thank you
We would welcome the chance to start in January.
EP
Engagement partner
name@westmonroe.com
DD
Delivery director
name@westmonroe.com
FL
Finance transformation lead
name@westmonroe.com
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 20
PROPOSAL FOR NORTHFIELD HEALTH SYSTEM
Close the books in five days
PREPARED BY
West Monroe · Finance Transformation
PROPOSAL CONTACTS
Engagement partner
name@westmonroe.com
Delivery director
name@westmonroe.com
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 21
PROPOSAL FOR NORTHFIELD HEALTH SYSTEM
Close the books in five days
PREPARED BY
West Monroe · Finance Transformation
PROPOSAL CONTACTS
Engagement partner
Delivery director
name@westmonroe.com
name@westmonroe.com
DATE
October 2026
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 22
RESPONSE TO RFP NHS-2026-014
Close the books in five days
PREPARED BY
West Monroe · Finance Transformation
PROPOSAL CONTACTS
Engagement partner
Delivery director
name@westmonroe.com
name@westmonroe.com
RESPONSE TO
RFP NHS-2026-014
ISSUED BY
Northfield Finance Office
SUBMITTED
October 2026
VALID THROUGH
31 January 2027
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 23
PROPOSAL · OCTOBER 2026
Close the books in five days
PREPARED BY
PROPOSAL CONTACTS
West Monroe
Finance Transformation
Engagement partner
name@westmonroe.com
Delivery director
name@westmonroe.com
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 24
PROPOSAL FOR NORTHFIELD HEALTH SYSTEM
The path to a five-day close
PREPARED BY
PROPOSAL CONTACTS
DATE
West Monroe
Finance Transformation
Engagement partner
name@westmonroe.com
Delivery director
name@westmonroe.com
October 2026
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 25
WORKSHOP · NORTHFIELD HEALTH SYSTEM
Close redesign working session
DATE
14 October 2026
LOCATION
Northfield main campus
WHO IS IN THE ROOM
Finance, shared services, IT
FACILITATED BY
Engagement partner · name@westmonroe.com
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 26
26
03
SECTION 03 OF 06
The solution
The operating model, tooling and controls that bring the close down to five days.
01
Our understanding
02
Approach
03
Solution
Target operating model
Systems and automation
Controls and audit readiness
Change and adoption
04
Team
05
Commercials
06
Why West Monroe
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 27
SECTION GUIDE · 03
Approach: how the work gets delivered
27
01 Context
02 Economics
03 Approach
04 Proof
05 Next steps
NARRATIVE OF THIS SECTION
Approved outcomes become working capability in four subphases. Design fixes the target, build and validation prove it with Northfield teams, and cutover moves entities in controlled waves behind leader sign-off.
SLIDE | TITLE | WHAT IT COVERS | WHEN TO USE
31 | Approach at a glance | Four subphases take approved outcomes to a live capability | Opening any delivery talk
32 | Subphase detail | Activities, outputs and owners for each subphase | Buyer asks for specifics
33 | Working model | What each Northfield team does, week by week | Resourcing questions
34 | Phased cutover | Entities move in controlled waves, not one event | Risk-averse operations leaders
35 | Decision gates | Where leaders sign off before work moves on | Steering committee review
36 | Delivery risks | Top risks and how we contain each one | Late-stage diligence
37 | Governance cadence | Who meets, how often and what they decide | Sponsor wants oversight
FOR INTERNAL USE
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 28
SECTION GUIDE · 03
Approach: how the work gets delivered
CONTEXT
ECONOMICS
APPROACH
PROOF
NEXT STEPS
28
NARRATIVE OF THIS SECTION
Approved outcomes become working capability in four subphases. Design fixes the target, build and validation prove it with Northfield teams, and cutover moves entities in controlled waves behind leader sign-off.
SLIDE | TITLE | WHAT IT COVERS | WHEN TO USE
31 | Approach at a glance | Four subphases take approved outcomes to a live capability | Opening any delivery talk
32 | Subphase detail | Activities, outputs and owners for each subphase | Buyer asks for specifics
33 | Working model | What each Northfield team does, week by week | Resourcing questions
34 | Phased cutover | Entities move in controlled waves, not one event | Risk-averse operations leaders
35 | Decision gates | Where leaders sign off before work moves on | Steering committee review
36 | Delivery risks | Top risks and how we contain each one | Late-stage diligence
37 | Governance cadence | Who meets, how often and what they decide | Sponsor wants oversight
FOR INTERNAL USE
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 29
SECTION OPENER · 03
Approach: how the work gets delivered
CONTEXT
ECONOMICS
APPROACH
PROOF
NEXT STEPS
29
SECTION 03 OF 05
Approved outcomes become working capability in four subphases.
Design fixes the target, build and validation prove it with Northfield teams, and cutover moves entities in controlled waves behind leader sign-off.
WHAT'S INSIDE
TIME TO PRESENT
Five slides, about 12 minutes.
31
Approach at a glance
Four subphases take approved outcomes to a live capability.
32
Subphase detail
Activities, outputs and owners for each subphase.
33
Working model
What each Northfield team does, week by week.
34
Phased cutover
Entities move in controlled waves, not one event.
35
Decision gates
Where leaders sign off before work moves on.
FOR INTERNAL USE
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 30
APPENDIX
Twelve appendix items, A1 to A12
30
REF | EXHIBIT | WHAT IT CONTAINS | PAGE
A1 | Interview summary | Who we spoke with and the themes that emerged | 65
A2 | Close calendar detail | Task-level calendar for each entity, day 1 to day 12 | 66
A3 | Entity-level findings | Findings and baselines for each of the eight entities | 67
A4 | Reconciliation inventory | All balance-sheet reconciliations with owners and frequency | 68
A5 | Process maps | Current-state and future-state maps for the close | 69
A6 | Systems inventory | Applications, interfaces and data owners in scope | 70
A7 | Control matrix | Key controls mapped to risks and audit assertions | 71
A8 | Detailed work plan | Activities, durations and dependencies by wave | 72
A9 | Fee build-up | How the phase fees are built from team and effort | 73
A10 | Staffing roster by role | Roles, allocation and timing across the three waves | 74
A11 | Glossary of terms | Definitions used throughout the proposal | 75
A12 | Case study detail | A comparable health system close transformation | 76
Pages 63 and 64 hold the appendix divider and this index.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 31
EXHIBITS
Twenty exhibits, figures and tables, by page
31
E01
Northfield entities and volumes
7
E02
Goals and success measures
8
E03
Close cycle by entity, days
9
E04
Where the days go in a close
11
E05
Root causes ranked by impact
12
E06
Three-wave approach
16
E07
Integrated timeline
20
E08
Governance structure
21
E09
Risks and mitigations
23
E10
Target operating model
27
E11
Close calendar, day by day
32
E12
Systems landscape
33
E13
Tooling options compared
35
E14
Recommended architecture
36
E15
Delivery team structure
46
E16
Fees by phase
51
E17
Business case
53
E18
Payback and sensitivity
54
E19
Comparable client results
58
E20
Client reference summary
60
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 32
SECTION 03 · SOLUTION
Solution: eighteen slides in three parts
UNDERSTAND
APPROACH
SOLUTION
TEAM
COMMERCIALS
WHY WM
32
3.1
Operating model
27–32
Target operating model
27
Process redesign overview
28
Reconciliation redesign
29
Intercompany simplification
30
Journal entry workflow
31
Close calendar: day by day
32
3.2
Technology
33–38
Systems landscape
33
Automation opportunities
34
Tooling options compared
35
Recommended architecture
36
Data and integration design
37
Reporting and dashboards
38
3.3
Readiness
39–44
Roles after the redesign
39
Controls and audit readiness
40
Training and enablement
41
Cutover plan
42
Hypercare and handover
43
Benefits tracking
44
Before: Approach, pages 15–26
After: Team, pages 45–50
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 33
SECTION INDEX
Seven sections, 76 pages: where each part sits
33
SECTION | WHAT IT COVERS | PAGES | SLIDES | SHARE OF DECK
Cover and indexes | Title page and the three-page slide index | 1–4 | 4 | 5%
Our understanding | Your goals, the close today and what success looks like | 5–14 | 10 | 13%
Approach | Three waves, timeline, governance and risks | 15–26 | 12 | 16%
Solution | Operating model, systems, controls and cutover | 27–44 | 18 | 24%
Team | Leadership, delivery team and your team's role | 45–50 | 6 | 8%
Commercials | Fees, assumptions, business case and next steps | 51–56 | 6 | 8%
Why West Monroe | Healthcare finance experience, results and references | 57–62 | 6 | 8%
Appendix | Twelve supporting exhibits, A1 to A12 | 63–76 | 14 | 18%
00
01
02
03
04
05
06
07
76 pages in all. Solution is the largest section at 18 slides; the appendix holds the supporting detail.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 34
SLIDE INDEX · CONTINUED
Every slide in the proposal, by section and page
34
03
Solution (continued)
27–44
Reconciliation redesign
29
Intercompany simplification
30
Journal entry workflow
31
Close calendar: day by day
32
Systems landscape
33
Automation opportunities
34
Tooling options compared
35
Recommended architecture
36
Data and integration design
37
Reporting and dashboards
38
Roles after the redesign
39
Controls and audit readiness
40
Training and enablement
41
03
Solution (continued)
27–44
Cutover plan
42
Hypercare and handover
43
Benefits tracking
44
04
Team
45–50
Engagement leadership
45
Delivery team structure
46
Core team profiles
47
Specialist advisors
48
Your team's role
49
Staffing by phase
50
05
Commercials
51–56
Fees by phase
51
Assumptions and dependencies
52
INDEX 2 OF 3
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 35
SLIDE INDEX · CONTINUED
Every slide in the proposal, by section and page
35
05
Commercials (continued)
51–56
Business case
53
Payback and sensitivity
54
Commercial terms
55
Next steps and timeline
56
06
Why West Monroe
57–62
Healthcare finance experience
57
Comparable client results
58
Our delivery model
59
Client references
60
Our commitments to you
61
Why West Monroe
62
07
Appendix
63–76
Appendix divider
63
07
Appendix (continued)
63–76
Appendix index
64
Interview summary
65
Close calendar detail
66
Entity-level findings
67
Reconciliation inventory
68
Process maps
69
Systems inventory
70
Control matrix
71
Detailed work plan
72
Fee build-up
73
Staffing roster by role
74
Glossary of terms
75
Case study detail
76
INDEX 3 OF 3
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 36
SLIDE INDEX
Every slide in the proposal, by section and page
36
01
Our understanding
5–14
Executive summary
5
What we heard from your leaders
6
Northfield at a glance
7
Goals for the next 24 months
8
The close cycle today
9
Pain points by entity
10
Where the days go
11
Root causes behind the delay
12
Constraints we will design around
13
What success looks like
14
02
Approach
15–26
Guiding principles
15
Our approach in three waves
16
02
Approach (continued)
15–26
Wave 1: stabilize the close
17
Wave 2: standardize entities
18
Wave 3: automate and sustain
19
Integrated timeline
20
Governance and cadence
21
Decision rights
22
Risks and mitigations
23
How we work with your team
24
Change and adoption plan
25
Quality and controls approach
26
03
Solution
27–44
Target operating model
27
Process redesign overview
28
INDEX 1 OF 3
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 37
SLIDE INDEX · THUMBNAILS
Team and commercials at a glance
37
04 TEAM · PAGES 45–50
45 · Engagement leadership
46 · Delivery team structure
47 · Core team profiles
48 · Specialist advisors
49 · Your team's role
50 · Staffing by phase
05 COMMERCIALS · PAGES 51–56
51 · Fees by phase
52 · Assumptions and dependencies
53 · Business case
54 · Payback and sensitivity
55 · Commercial terms
56 · Next steps and timeline
PAGES 45–56
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 38
SLIDE INDEX WITH TYPE
Every slide with its type and page
38
SLIDE | TITLE | TYPE | PAGE
1.1 | Executive summary | SUMMARY | 5
1.2 | What we heard from your leaders | INSIGHT | 6
1.3 | Northfield at a glance | CONTEXT | 7
1.4 | Goals for the next 24 months | GOALS | 8
1.5 | The close cycle today | DIAGNOSTIC | 9
1.6 | Pain points by entity | TABLE | 10
1.7 | Where the days go | CHART | 11
1.8 | Root causes behind the delay | DIAGNOSTIC | 12
1.9 | Constraints we will design around | CONSTRAINTS | 13
1.10 | What success looks like | OUTCOMES | 14
2.1 | Guiding principles | PRINCIPLES | 15
2.2 | Our approach in three waves | PLAN | 16
2.3 | Wave 1: stabilize the close | PLAN | 17
2.4 | Wave 2: standardize entities | PLAN | 18
2.5 | Wave 3: automate and sustain | PLAN | 19
2.6 | Integrated timeline | TIMELINE | 20
UNDERSTANDING
APPROACH
SLIDES 5–20 OF 76
INDEX 1 OF 5
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 39
SLIDE INDEX WITH TYPE · CONTINUED
Every slide with its type and page
39
SLIDE | TITLE | TYPE | PAGE
2.7 | Governance and cadence | GOVERNANCE | 21
2.8 | Decision rights | DECISION | 22
2.9 | Risks and mitigations | RISK | 23
2.10 | How we work with your team | APPROACH | 24
2.11 | Change and adoption plan | CHANGE | 25
2.12 | Quality and controls approach | CONTROLS | 26
3.1 | Target operating model | MODEL | 27
3.2 | Process redesign overview | PROCESS | 28
3.3 | Reconciliation redesign | PROCESS | 29
3.4 | Intercompany simplification | PROCESS | 30
3.5 | Journal entry workflow | PROCESS | 31
3.6 | Close calendar: day by day | TIMELINE | 32
3.7 | Systems landscape | ARCHITECTURE | 33
3.8 | Automation opportunities | TABLE | 34
3.9 | Tooling options compared | COMPARISON | 35
3.10 | Recommended architecture | ARCHITECTURE | 36
APPROACH
SOLUTION
CONTINUED · SLIDES 21–36 OF 76
INDEX 2 OF 5
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 40
TOPIC INDEX
Find any topic, A to Z, by page
40
A
Adoption plan
25, 41
Approach waves
16–19
Audit readiness
40, 71
Automation
19, 34, 36
B
Benefits tracking
44, 53
Business case
53–54
C
Case studies
58, 76
Change impact
25, 39
Close calendar
9, 32, 66
Commercial terms
55
Controls
26, 40, 71
Cutover
20, 42–43
D
Dashboards
38
Data migration
37, 42
Decision rights
22
E
Entity findings
10, 67
Executive summary
5
F
Fees
51, 73
Financial close
9–12
G
Glossary
75
Governance
21–22
H
Healthcare finance
57
Hypercare
43
I
Integration
37
Intercompany
30
Interviews
6, 65
J
Journal entries
31
K
Key dependencies
52
L
Leadership team
45
M
Milestones
20, 56
N
Next steps
56
O
Operating model
27, 39
P
Payback
54
Process maps
69
Q
Quality reviews
26
R
Reconciliations
29, 68
References
60
Risks
23
S
Staffing
50, 74
Systems
33, 70
T
Team profiles
47–48
Timeline
20, 56
Training
41
V
Value drivers
8, 54
W
Work plan
72
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 41
CRITICAL PATH
Build and UAT carry no float; feeders have a week or two
41
FEEDER WORK · FLOAT
CRITICAL PATH · ZERO FLOAT
Critical link
Feeds, with float
22 JAN
WEEK 2
Mobilize complete
Team, governance and plan in place; steering committee chartered.
5 FEB
WEEK 4
Current state signed off
Access and revenue cycle baseline agreed with operations leads.
Data access granted
29 JAN · 1 WK FLOAT
26 FEB
WEEK 7
Design approved
Future-state scheduling, registration and billing design approved.
Business case
19 FEB · 1 WK FLOAT
26 MAR
WEEK 11
Build complete
Workflows, rules and interfaces configured and unit tested.
Interface specs signed
12 MAR · 2 WK FLOAT
16 APR
WEEK 14
UAT exit
Users pass every critical script with no open severity 1 or 2 defects.
Test scripts ready
26 MAR · 1 WK FLOAT
30 APR
WEEK 16
Go-live wave 1
Central scheduling and two hospitals move to the new workflows.
Training delivered
23 APR · 1 WK FLOAT
28 MAY
WEEK 20
Go-live wave 2
The remaining hospitals and ambulatory clinics go live.
Wave 2 readiness
21 MAY · 1 WK FLOAT
25 JUN
WEEK 24
Hypercare exit
KPIs stable for four weeks; support handed to Northfield teams.
Benefits checkpoint
18 JUN · 1 WK FLOAT
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 42
PROGRAM STATUS
Two milestones slip a week, but the 30 Apr go-live holds
42
STATUS AT 19 MAR · WEEK 10 OF 24
Done
On track
At risk
Baseline to forecast
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
W15
W16
W17
W18
W19
W20
W21
W22
W23
W24
TODAY
M1
M2
M3
M4
M5
M6
M7
M8
MILESTONE | BASELINE | FORECAST | VARIANCE | STATUS
Mobilize complete | 22 Jan | 22 Jan | On plan | Done
Current state signed off | 5 Feb | 5 Feb | On plan | Done
Design approved | 26 Feb | 26 Feb | On plan | Done
Build complete | 26 Mar | 2 Apr | +1 wk | At risk
UAT exit | 16 Apr | 23 Apr | +1 wk | At risk
Go-live wave 1 | 30 Apr | 30 Apr | On plan | On track
Go-live wave 2 | 28 May | 28 May | On plan | On track
Hypercare exit | 25 Jun | 25 Jun | On plan | On track
M1
M2
M3
M4
M5
M6
M7
M8
VARIANCE TO BASELINE
Build and UAT slip one week
Clearinghouse interface rework adds a week to build.
Six-day UAT weeks recover it, so go-live holds at 30 Apr.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 43
MILESTONE REGISTER
Four of 26 milestones are forecast a week late
43
ID | MILESTONE | BASELINE | FORECAST | DESCRIPTION | OWNER | STATUS
MS-01 | Mobilize complete | 22 Jan | 22 Jan | Team, governance and plan in place | PMO lead | Done
MS-02 | Data access granted | 29 Jan | 29 Jan | Read access to scheduling and billing data | IT applications lead | Done
MS-03 | Interviews complete | 29 Jan | 29 Jan | Leads interviewed at every site | VP patient access | Done
MS-04 | Current state signed off | 5 Feb | 5 Feb | Access and revenue cycle baseline agreed | VP patient access | Done
MS-05 | Baseline KPIs agreed | 12 Feb | 12 Feb | No-show, denial and cash KPIs baselined | VP revenue cycle | Done
MS-06 | Future-state design drafted | 19 Feb | 19 Feb | Scheduling, registration and billing designs | Design lead | Done
MS-07 | Business case approved | 26 Feb | 26 Feb | Benefits and run cost approved by the CFO | CFO | Done
MS-08 | Design approved | 26 Feb | 26 Feb | Steering committee signs the design | Steering committee | Done
MS-09 | Build specifications signed | 5 Mar | 5 Mar | Configuration specs for every workflow | IT applications lead | Done
MS-10 | Configuration demo | 12 Mar | 12 Mar | First workflows shown to operations leads | Product owner | Done
MS-11 | Interface specs signed | 12 Mar | 19 Mar | Clearinghouse and EHR specs agreed | Integration lead | Done
MS-12 | Test plan approved | 19 Mar | 19 Mar | SIT and UAT scope and entry criteria | Test lead | Done
MS-13 | Test scripts ready | 26 Mar | 26 Mar | Critical UAT scripts written and reviewed | Test lead | On track
MS-14 | Build complete | 26 Mar | 2 Apr | Workflows, rules and interfaces unit tested | IT applications lead | At risk
M1
M2
M3
M4
PHASE 1
PHASE 2
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 44
MILESTONE REGISTER
Deployment milestones hold to the baseline dates
44
ID | MILESTONE | BASELINE | FORECAST | DESCRIPTION | OWNER | STATUS
MS-15 | Data conversion trial 2 | 2 Apr | 9 Apr | Second full load reconciled to source totals | Data lead | At risk
MS-16 | SIT exit | 9 Apr | 9 Apr | End-to-end flows pass across all interfaces | Test lead | On track
MS-17 | UAT exit | 16 Apr | 23 Apr | No open severity 1 or 2 defects | Test lead | At risk
MS-18 | Training delivered | 23 Apr | 23 Apr | Wave 1 staff trained in the new workflows | Change lead | On track
MS-19 | Cutover rehearsal complete | 23 Apr | 23 Apr | Dress rehearsal inside the cutover window | Cutover lead | On track
MS-20 | Go/no-go decision | 27 Apr | 27 Apr | Steering committee confirms readiness | Steering committee | On track
MS-21 | Go-live wave 1 | 30 Apr | 30 Apr | Central scheduling and two hospitals go live | Program director | On track
MS-22 | Wave 1 stabilized | 14 May | 14 May | Queues and work lists back to baseline | Hypercare lead | On track
MS-23 | Wave 2 readiness confirmed | 21 May | 21 May | Sites, users and data ready for wave 2 | Change lead | On track
MS-24 | Go-live wave 2 | 28 May | 28 May | Remaining hospitals and clinics go live | Program director | On track
MS-25 | Benefits checkpoint | 18 Jun | 18 Jun | KPIs measured against the business case | VP revenue cycle | On track
MS-26 | Hypercare exit | 25 Jun | 25 Jun | Support handed to Northfield teams | VP revenue cycle | On track
M5
M6
M7
M8
PHASE 2
PHASE 3
MILESTONE REGISTER, CONTINUED · 2 OF 2
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 45
WORK PLAN
Eight gates, two go-live waves
45
WORKSTREAM · WEEK
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
ASSESS AND DESIGN
BUILD AND TEST
DEPLOY AND STABILIZE
GATES
Key milestones
M1–M8, right
M1
M2
M3
M4
M5
M6
M7
M8
WORKSTREAMS
Patient access
Scheduling
Assess, design
Build and test
Waves 1–2
Revenue cycle
Billing, claims
Baseline
Build rules
Rollout
Technology
Interfaces, data
Interfaces
Build, SIT
Cutover
Support
Testing
SIT and UAT
Test, UAT
Regression
Change
Comms, training
Comms plan
Training
Train users
Program
PMO, steering
Plan, risks, steering committee every two weeks
Assess and design
Build and test
Deploy and stabilize
Support and governance
First go-live
Milestone
M1
Mobilize complete
22 Jan · Team and plan in place
M2
Current state signed off
5 Feb · Baseline agreed
M3
Design approved
26 Feb · Future state approved
M4
Build complete
26 Mar · Configured and unit tested
M5
UAT exit
16 Apr · No open severity 1–2 defects
M6
Go-live wave 1
30 Apr · Central scheduling, two hospitals
M7
Go-live wave 2
28 May · All hospitals and clinics
M8
Hypercare exit
25 Jun · KPIs stable, support handed over
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 46
WORK PLAN
Eight gates hold the plan to a 24-week finish
46
WORKSTREAM · WEEK
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
W15
W16
W17
W18
W19
W20
W21
W22
W23
W24
ASSESS AND DESIGN
BUILD AND TEST
DEPLOY AND STABILIZE
GATES
Key milestones
Keyed M1–M8 below
M1
M2
M3
M4
M5
M6
M7
M8
WORK
Patient access
Scheduling, registration
Current state
Design
Build
Test
Waves 1 and 2
Revenue cycle
Billing, claims, denials
Baseline
Design
Build rules
UAT
Rollout and tuning
Technology
Interfaces, data, cutover
Set-up
Interfaces
Build, SIT
Data
Cutover
Assess and design
Build and test
Deploy and stabilize
First go-live
Milestone
M1
Mobilize complete
22 JAN
Team and plan in place
M2
Current state signed off
5 FEB
Baseline agreed
M3
Design approved
26 FEB
Future state approved
M4
Build complete
26 MAR
Configured and tested
M5
UAT exit
16 APR
Critical scripts passed
M6
Go-live wave 1
30 APR
Two hospitals live
M7
Go-live wave 2
28 MAY
All sites live
M8
Hypercare exit
25 JUN
Support handed over
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 47
PROGRAM TIMELINE
Eight milestones take the program live in 24 weeks
47
PHASE 1 · ASSESS AND DESIGN
W1–W7 · 11 JAN – 26 FEB
PHASE 2 · BUILD AND TEST
W8–W14 · 1 MAR – 16 APR
PHASE 3 · DEPLOY AND STABILIZE
W15–W24 · 19 APR – 25 JUN
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
W15
W16
W17
W18
W19
W20
W21
W22
W23
W24
M1 · 22 JAN
Mobilize complete
Team, governance and plan in place; steering committee chartered.
M2 · 5 FEB
Current state signed off
Access and revenue cycle baseline agreed with operations leads.
M3 · 26 FEB
Design approved
Future-state scheduling, registration and billing design approved.
M4 · 26 MAR
Build complete
Workflows, rules and interfaces configured and unit tested.
M5 · 16 APR
UAT exit
Users pass every critical script with no open severity 1 or 2 defects.
M6 · 30 APR
Go-live wave 1
Central scheduling and two hospitals move to the new workflows.
M7 · 28 MAY
Go-live wave 2
The remaining hospitals and ambulatory clinics go live.
M8 · 25 JUN
Hypercare exit
KPIs stable for four weeks; support handed to Northfield teams.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 48
PHASE 2 · BUILD AND TEST
Build and test closes on two milestones in seven weeks
OVERVIEW
ASSESS
BUILD
DEPLOY
48
PHASE 2 OF 3 · WEEKS 8–14 · 1 MAR – 16 APR
Configure, integrate and prove the new workflows. The phase ends when business users pass UAT.
W8
W9
W10
W11
W12
W13
W14
Build specs
Interface specs
Test plan
M4 · Build complete
SIT exit
M5 · UAT exit
M4 · 26 MAR · WEEK 11
Build complete
Workflows, rules and interfaces configured and unit tested.
EXIT CRITERIA
All stories accepted
Interfaces pass unit tests
M5 · 16 APR · WEEK 14
UAT exit
Business users pass every critical script.
EXIT CRITERIA
No open severity 1 or 2 defects
Cutover runbook rehearsed
CHECKPOINTS IN THIS PHASE
5 MAR
Build specs signed
Configuration specs for every workflow
12 MAR
Interface specs signed
Clearinghouse and EHR specs agreed
19 MAR
Test plan approved
SIT and UAT scope and entry criteria
9 APR
SIT exit
End-to-end flows pass on all interfaces
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 49
APPROACH
Every phase ends on milestones the steering group signs
49
PHASE 1 · W1–W7 · 11 JAN – 26 FEB
Assess and design
M1 · 22 JAN · WEEK 2
Mobilize complete
Team, governance and plan in place.
M2 · 5 FEB · WEEK 4
Current state signed off
Baseline agreed with operations leads.
M3 · 26 FEB · WEEK 7
Design approved
Steering committee approves the future state.
EXIT CRITERIA
Current state and design signed off
Business case approved by the CFO
PHASE 2 · W8–W14 · 1 MAR – 16 APR
Build and test
C1 · 12 MAR · WEEK 9
Configuration demo
First workflows shown to operations leads.
M4 · 26 MAR · WEEK 11
Build complete
Workflows, rules and interfaces unit tested.
M5 · 16 APR · WEEK 14
UAT exit
No open severity 1 or 2 defects remain.
EXIT CRITERIA
Every critical UAT script passed
Cutover runbook rehearsed end to end
PHASE 3 · W15–W24 · 19 APR – 25 JUN
Deploy and stabilize
M6 · 30 APR · WEEK 16
Go-live wave 1
Central scheduling and two hospitals go live.
M7 · 28 MAY · WEEK 20
Go-live wave 2
Remaining hospitals and clinics go live.
M8 · 25 JUN · WEEK 24
Hypercare exit
Support handed to Northfield teams.
EXIT CRITERIA
Both waves live at every site
KPIs stable for four weeks
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 50
PROGRAM CALENDAR
Two milestones land in February and two in April
50
Q1 · W1–W3
January
M1 · 22 JAN
Mobilize complete
Team, governance and plan in place; steering committee chartered.
PMO LEAD
DELIVERABLES
Mobilization plan
Governance charter
Q1 · W4–W7
February
M2 · 5 FEB
Current state signed off
Baseline agreed with operations leads.
VP PATIENT ACCESS
M3 · 26 FEB
Design approved
Steering committee approves the future state.
STEERING COMMITTEE
Q1 · W8–W12
March
M4 · 26 MAR
Build complete
Workflows, rules and interfaces configured and unit tested.
IT APPLICATIONS LEAD
DELIVERABLES
Build specifications
Configured workflows
Q2 · W13–W16
April
M5 · 16 APR
UAT exit
No open severity 1 or 2 defects remain.
TEST LEAD
M6 · 30 APR
Go-live wave 1
Central scheduling and two hospitals go live.
PROGRAM DIRECTOR
Q2 · W17–W20
May
M7 · 28 MAY
Go-live wave 2
The remaining hospitals and ambulatory clinics go live.
PROGRAM DIRECTOR
DELIVERABLES
Wave 2 readiness
Q2 · W21–W24
June
M8 · 25 JUN
Hypercare exit
KPIs stable for four weeks; support handed to Northfield teams.
VP REVENUE CYCLE
DELIVERABLES
Hypercare report
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 51
PROGRAM TIMELINE
Each milestone closes with the deliverables that prove it
51
22 JAN
WEEK 2
Mobilize complete
Team, governance and plan in place; steering committee chartered.
MOBILIZATION PLAN
GOVERNANCE CHARTER
5 FEB
WEEK 4
Current state signed off
Access and revenue cycle baseline agreed with operations leads.
CURRENT-STATE REPORT
BASELINE KPIS
26 FEB
WEEK 7
Design approved
Future-state scheduling, registration and billing design approved.
FUTURE-STATE DESIGN
BUSINESS CASE
26 MAR
WEEK 11
Build complete
Workflows, rules and interfaces configured and unit tested.
BUILD SPECIFICATIONS
CONFIGURED WORKFLOWS
16 APR
WEEK 14
UAT exit
Users pass every critical script with no open severity 1 or 2 defects.
TEST PLAN
UAT SIGN-OFF
30 APR
WEEK 16
Go-live wave 1
Central scheduling and two hospitals move to the new workflows.
TRAINING MATERIALS
CUTOVER RUNBOOK
28 MAY
WEEK 20
Go-live wave 2
The remaining hospitals and ambulatory clinics go live.
WAVE 2 READINESS
25 JUN
WEEK 24
Hypercare exit
KPIs stable for four weeks; support handed to Northfield teams.
HYPERCARE REPORT
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 52
PROGRAM TIMELINE
Two go-live waves in 24 weeks, each gated
52
A 24-week program moves scheduling, registration and billing at Northfield onto one set of workflows, live in two waves.
W1–W7 · 11 JAN – 26 FEB
Assess and design
Baseline, future-state design and business case.
W8–W14 · 1 MAR – 16 APR
Build and test
Configure, integrate and prove it in UAT.
W15–W24 · 19 APR – 25 JUN
Deploy and stabilize
Two go-live waves, then four weeks of hypercare.
22 JAN
WEEK 2
Mobilize complete
Team, governance and plan in place.
MOBILIZATION PLAN
GOVERNANCE CHARTER
5 FEB
WEEK 4
Current state signed off
Baseline agreed with operations leads.
CURRENT-STATE REPORT
BASELINE KPIS
26 FEB
WEEK 7
Design approved
Steering committee approves the future state.
FUTURE-STATE DESIGN
BUSINESS CASE
26 MAR
WEEK 11
Build complete
Workflows, rules and interfaces unit tested.
BUILD SPECIFICATIONS
CONFIGURED WORKFLOWS
16 APR
WEEK 14
UAT exit
No open severity 1 or 2 defects remain.
TEST PLAN
UAT SIGN-OFF
30 APR
WEEK 16
Go-live wave 1
Central scheduling and two hospitals go live.
TRAINING MATERIALS
CUTOVER RUNBOOK
28 MAY
WEEK 20
Go-live wave 2
Remaining hospitals and clinics go live.
WAVE 2 READINESS
25 JUN
WEEK 24
Hypercare exit
Support handed to Northfield teams.
HYPERCARE REPORT
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 53
DELIVERABLE ACCEPTANCE · WEEK 11
Four deliverables are accepted and three are in review
53
DELIVERABLE | DUE | REVIEWER | APPROVER | ACCEPTANCE CRITERIA | STATUS
Program charter and plan | W2 · Nov 13 | PMO lead | Steering committee | Scope, plan, RACI signed by sponsor | Accepted
Stakeholder and change map | W2 · Nov 13 | Access director | PMO lead | All 6 sites and 14 roles mapped | Accepted
Current-state assessment | W6 · Dec 11 | Revenue cycle VP | Steering committee | Validated in 3 site walk-throughs | Accepted
Baseline metrics pack | W6 · Dec 11 | Finance director | CFO | 12 months reconciled to the GL | Accepted
Future-state design | W10 · Jan 8 | Revenue cycle VP | Steering committee | Every design decision has an owner | In review
Business case | W10 · Jan 8 | Finance director | CFO | Benefits tied to the baseline pack | In review
Build specifications | W15 · Feb 12 | WM architect | CIO | Specs traced to approved design | In review
Test plan and scripts | W15 · Feb 12 | QA manager | CIO | Scripts cover all in-scope flows | Not started
UAT exit report | W17 · Feb 26 | QA manager | Steering committee | No open severity 1 or 2 defects | Not started
Training materials | W18 · Mar 5 | Access director | Revenue cycle VP | 90% of wave 1 staff trained | Not started
Cutover runbook | W18 · Mar 5 | IT apps lead | CIO | Two dress rehearsals run to time | Not started
Wave 2 readiness review | W21 · Mar 26 | PMO lead | Steering committee | All wave 2 sites scored ready | Not started
Hypercare report | W24 · Apr 16 | PMO lead | Steering committee | Metrics stable for 4 weeks | Not started
D01
D02
D03
D04
D05
D06
D07
D08
D09
D10
D11
D12
D13
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 54
MILESTONES AND DELIVERABLES
Six milestones carry the program to a stable go-live
54
M2 · W6 · DEC 11
Current state signed off
Assessment findings and the baseline are accepted.
Assessment: 6 areas
Baseline: denials, AR, cash
M3 · W10 · JAN 8
Design approved
Target processes and the business case are approved.
Design: processes, roles
Business case: payback
M4 · W15 · FEB 12
Build complete
Configuration, interfaces and reports are built and unit tested.
Build specs: traced to design
Test pack: 320 scripts
M5 · W17 · FEB 26
UAT exit
Users accept the build and the go decision is recorded.
UAT exit report: no Sev 1 or 2
Defect log: owners, dates
M6 · W18 · MAR 5
Go-live wave 1
Three sites go live with trained staff and a command center.
Training: role guides
Runbook: rollback plan
M8 · W24 · APR 16
Hypercare exit
Metrics hold at baseline and support takes over.
Hypercare report: 4 weeks stable
Handover: to support
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 55
MILESTONES AND DELIVERABLES
Four sign-offs gate the program, each backed by named deliverables
55
The steering committee meets the week after each sign-off. Deliverables reach members five working days before.
PHASE 1 · W1–W6
Assess
2 milestones · 4 deliverables
PHASE 2 · W7–W17
Design and build
3 milestones · 5 deliverables
PHASE 3 · W18–W24
Deploy and stabilize
3 milestones · 4 deliverables
M2 · W6 · DEC 11
Current state signed off
Findings and baseline accepted.
Current-state assessment: 6 areas
Baseline metrics pack: 12 months
Change map: 14 roles
Site walk-throughs: 3 sites
M3 · W10 · JAN 8
Design approved
Target design and business case approved.
Future-state design: processes, roles
Business case: payback by wave
Decision log: 42 decisions
Workshop outputs: 4 sessions
M5 · W17 · FEB 26
UAT exit
Users accept the build; go decision recorded.
UAT exit report: no Sev 1 or 2
Defect log: owners, dates
Build specifications: as built
Cutover runbook: rehearsed
M8 · W24 · APR 16
Hypercare exit
Metrics stable; support takes over.
Hypercare report: 4 weeks stable
Wave 2 readiness: lessons applied
Support handover: signed
Lessons learned: both waves
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 56
MILESTONES AND DELIVERABLES
Milestones and deliverables: mobilize to build complete
56
DELIVERABLE | DESCRIPTION | FORMAT | OWNER | APPROVER
M1 · MOBILIZE COMPLETE · W2 · NOV 13 |  |  |  | 
Program charter and plan | Scope, governance and 24-week plan | PLAN | WM program lead | Steering committee
Stakeholder and change map | Roles, impacts and cadence by site | WORKBOOK | WM change lead | PMO lead
M2 · CURRENT STATE SIGNED OFF · W6 · DEC 11 |  |  |  | 
Current-state assessment | Process, systems and data baseline | REPORT | WM process lead | Steering committee
Baseline metrics pack | Denials, errors, cash and days in AR | DASHBOARD | WM analytics lead | CFO
M3 · DESIGN APPROVED · W10 · JAN 8 |  |  |  | 
Future-state design | Target processes, roles and systems | DESIGN DOC | WM design lead | Steering committee
Business case | Benefits, cost and payback by wave | MODEL | WM program lead | CFO
M4 · BUILD COMPLETE · W15 · FEB 12 |  |  |  | 
Build specifications | Configuration, interface, report specs | SPECS | IT apps lead | CIO
Test plan and scripts | Entry and exit criteria, 320 scripts | TEST PACK | WM test lead | CIO
D01
D02
D03
D04
D05
D06
D07
D08
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 57
MILESTONES AND DELIVERABLES
Milestones and deliverables: UAT exit to hypercare exit
57
DELIVERABLE | DESCRIPTION | FORMAT | OWNER | APPROVER
M5 · UAT EXIT · W17 · FEB 26 |  |  |  | 
Test plan and scripts, final | Rerun results and the defect log | TEST PACK | WM test lead | CIO
UAT exit report | Results, defects, go or no-go view | REPORT | WM test lead | Steering committee
M6 · GO-LIVE WAVE 1 · W18 · MAR 5 |  |  |  | 
Training materials | Role guides, e-learning, super-users | COURSEWARE | Training lead | Revenue cycle VP
Cutover runbook | Cutover, rollback, command center | RUNBOOK | WM cutover lead | CIO
M7 · GO-LIVE WAVE 2 · W21 · MAR 26 |  |  |  | 
Wave 2 readiness review | Site readiness, wave 1 lessons | SCORECARD | WM change lead | Steering committee
Cutover runbook, wave 2 | Updated for wave 2 sites and lessons | RUNBOOK | WM cutover lead | CIO
M8 · HYPERCARE EXIT · W24 · APR 16 |  |  |  | 
Hypercare report | Stability metrics, support handover | REPORT | WM program lead | Steering committee
D08
D09
D10
D11
D12
D11
D13
MILESTONES AND DELIVERABLES · CONTINUED
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 58
DELIVERABLE D05
Future-state design: the blueprint the build is held to
58
PURPOSE
Sets the target processes, roles and system changes the build is specified, tested and accepted against.
FORMAT
Design document, about 60 pages
AUDIENCE
Steering committee, area leads, IT
SUPPORTS M3 · W10 · JAN 8
Design approved
WHAT IT CONTAINS
01
Design principles
Eight rules every decision is tested against
02
Future-state processes
Scheduling to cash posting, 6 areas
03
Roles and staffing
Who does each step, by site
04
System changes
Configuration, interfaces and reports
05
Decision log
42 decisions, each with an owner
06
Benefits link
Each change tied to a baseline metric
INPUTS AND DEPENDENCIES
Current-state assessment (D03), signed off W6
Baseline metrics pack (D04)
Design workshops four, weeks 7 to 9
Vendor roadmap from IT apps lead
REVIEW AND ACCEPTANCE
Draft to area leads
W8 · DEC 25
Revenue cycle VP review
W9 · JAN 1
Steering committee approval
W10 · JAN 8
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 59
MILESTONES AND DELIVERABLES
Thirteen deliverables, each owned and reviewed
59
DELIVERABLE | DESCRIPTION | FORMAT | DUE | OWNER | REVIEWER
Program charter and plan | Scope, governance and 24-week plan | PLAN | M1 · W2 | WM program lead | PMO lead
Stakeholder and change map | Roles, impacts and cadence by site | WORKBOOK | M1 · W2 | WM change lead | Access director
Current-state assessment | Process, systems and data baseline | REPORT | M2 · W6 | WM process lead | Revenue cycle VP
Baseline metrics pack | Denials, errors, cash and days in AR | DASHBOARD | M2 · W6 | WM analytics lead | Finance director
Future-state design | Target processes, roles and systems | DESIGN DOC | M3 · W10 | WM design lead | Revenue cycle VP
Business case | Benefits, cost and payback by wave | MODEL | M3 · W10 | WM program lead | Finance director
Build specifications | Configuration, interface, report specs | SPECS | M4 · W15 | IT apps lead | WM architect
Test plan and scripts | Entry and exit criteria, 320 scripts | TEST PACK | M4 · W15 | WM test lead | QA manager
UAT exit report | Results, defects, go or no-go view | REPORT | M5 · W17 | WM test lead | QA manager
Training materials | Role guides, e-learning, super-users | COURSEWARE | M6 · W18 | Training lead | Access director
Cutover runbook | Cutover, rollback, command center | RUNBOOK | M6 · W18 | WM cutover lead | IT apps lead
Wave 2 readiness review | Site readiness, wave 1 lessons | SCORECARD | M7 · W21 | WM change lead | PMO lead
Hypercare report | Stability metrics, support handover | REPORT | M8 · W24 | WM program lead | PMO lead
D01
D02
D03
D04
D05
D06
D07
D08
D09
D10
D11
D12
D13
ASSESS
DESIGN AND BUILD
DEPLOY
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 60
MILESTONES AND DELIVERABLES
Hypercare exit re-tests the baseline and business case
60
 |  | ASSESS |  | DESIGN AND BUILD |  |  | DEPLOY |  | 
DELIVERABLE | DESCRIPTION | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8
Program charter and plan | Scope, governance and 24-week plan |  |  |  |  |  |  |  | 
Stakeholder and change map | Roles, impacts and cadence by site |  |  |  |  |  |  |  | 
Current-state assessment | Process, systems and data baseline |  |  |  |  |  |  |  | 
Baseline metrics pack | Denials, errors, cash and days in AR |  |  |  |  |  |  |  | 
Future-state design | Target processes, roles and systems |  |  |  |  |  |  |  | 
Business case | Benefits, cost and payback by wave |  |  |  |  |  |  |  | 
Build specifications | Configuration, interface, report specs |  |  |  |  |  |  |  | 
Test plan and scripts | Entry and exit criteria, 320 scripts |  |  |  |  |  |  |  | 
UAT exit report | Results, defects, go or no-go view |  |  |  |  |  |  |  | 
Training materials | Role guides, e-learning, super-users |  |  |  |  |  |  |  | 
Cutover runbook | Cutover, rollback, command center |  |  |  |  |  |  |  | 
Wave 2 readiness review | Site readiness, wave 1 lessons |  |  |  |  |  |  |  | 
Hypercare report | Stability metrics, support handover |  |  |  |  |  |  |  | 
D01
D02
D03
D04
D05
D06
D07
D08
D09
D10
D11
D12
D13
M1 MOBILIZE COMPLETE · W2
M2 CURRENT STATE SIGNED OFF · W6
M3 DESIGN APPROVED · W10
M4 BUILD COMPLETE · W15
M5 UAT EXIT · W17
M6 GO-LIVE WAVE 1 · W18
M7 GO-LIVE WAVE 2 · W21
M8 HYPERCARE EXIT · W24
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 61
MILESTONES AND DELIVERABLES
Eight milestones over 24 weeks, each with its deliverables
APPROACH
MILESTONES
TEAM
COMMERCIALS
61
M1 · W2 · NOV 13
Mobilize complete
Charter and plan
Change map
SIGN-OFF · SPONSOR
M2 · W6 · DEC 11
Baseline signed off
Current-state assessment
Baseline metrics
SIGN-OFF · STEERING
M3 · W10 · JAN 8
Design approved
Future-state design
Business case
SIGN-OFF · STEERING
M4 · W15 · FEB 12
Build complete
Build specifications
Test plan, 320 scripts
SIGN-OFF · CIO
M5 · W17 · FEB 26
UAT exit
UAT exit report
Go decision record
SIGN-OFF · STEERING
M6 · W18 · MAR 5
Go-live wave 1
Training materials
Cutover runbook
SIGN-OFF · GO-LIVE BOARD
M7 · W21 · MAR 26
Go-live wave 2
Wave 2 readiness review
Runbook update
SIGN-OFF · GO-LIVE BOARD
M8 · W24 · APR 16
Hypercare exit
Hypercare report
Support handover
SIGN-OFF · STEERING
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 62
MILESTONES AND DELIVERABLES
Each phase closes on milestones its deliverables prove
62
PHASE 1 · W1–W6
Assess
MILESTONES
Nov 13
M1 Mobilize complete
Dec 11
M2 Current state signed off
DELIVERABLES
Charter and plan: scope, RACI, plan
Change map: 14 roles, 6 sites
Current-state assessment: 6 areas
Baseline metrics: 12 months, reconciled
Exit: findings and baseline accepted
PHASE 2 · W7–W17
Design and build
MILESTONES
Jan 8
M3 Design approved
Feb 12
M4 Build complete
Feb 26
M5 UAT exit
DELIVERABLES
Future-state design: processes, roles
Business case: payback by wave
Build specifications: traced to design
Test plan: 320 scripts
UAT exit report: go or no-go
Exit: go decision recorded at UAT
PHASE 3 · W18–W24
Deploy and stabilize
MILESTONES
Mar 5
M6 Go-live wave 1
Mar 26
M7 Go-live wave 2
Apr 16
M8 Hypercare exit
DELIVERABLES
Training materials: role guides, e-learning
Cutover runbook: rollback, command center
Wave 2 readiness: 6 sites scored
Hypercare report: handover to support
Exit: support signs the handover
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 63
MILESTONES AND DELIVERABLES
Eight milestones, each proved by named deliverables
63
MILESTONE | DATE | DELIVERABLES | OWNER | ACCEPTANCE CRITERIA
Mobilize complete | W2 · Nov 13 | Charter and plan: scope, RACI, 24-week plan Change map: roles and impacts by site | WM program lead | Sponsor signs charter; team and data access in place
Current state signed off | W6 · Dec 11 | Current-state assessment: 6 areas Baseline metrics: denials, AR, cash | Revenue cycle VP | Steering committee accepts findings and baseline
Design approved | W10 · Jan 8 | Future-state design: processes and roles Business case: payback by wave | WM design lead | All design decisions logged; CFO accepts business case
Build complete | W15 · Feb 12 | Build specs: config, interfaces, reports Test plan: 320 scripts | IT apps lead | All specs built and unit tested; test pack ready
UAT exit | W17 · Feb 26 | UAT exit report: go or no-go recommendation | WM test lead | No open severity 1 or 2 defects; go decision recorded
Go-live wave 1 | W18 · Mar 5 | Training: role guides, super-user kit Cutover runbook: rollback, command center | WM cutover lead | Wave 1 sites live; 90% of staff trained
Go-live wave 2 | W21 · Mar 26 | Wave 2 readiness review: 6 sites scored | WM change lead | Wave 2 sites live; wave 1 issues closed
Hypercare exit | W24 · Apr 16 | Hypercare report: handover to support | PMO lead | Metrics at baseline or better for four weeks
M1
M2
M3
M4
M5
M6
M7
M8
ASSESS
DESIGN AND BUILD
DEPLOY
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 64
WORK PLAN
Eight weeks from kickoff to a signed-off roadmap
64
WORKSTREAM · ACTIVITY
W1
OCT 5
W2
OCT 12
W3
OCT 19
W4
OCT 26
W5
NOV 2
W6
NOV 9
W7
NOV 16
W8
NOV 23
MOBILIZE
DIAGNOSE
DESIGN
ROADMAP
G1 · MOBILIZED
G2 · READOUT
G3 · FINAL
FINANCE
Current-state diagnostic
Interviews, close calendar
Interviews and close mapping
Controller workshop
Future-state design
Operating model
Design sprints
Design review
Roadmap and business case
Waves, value, cost
Roadmap
DATA
Systems and architecture
14 business units
Systems inventory
Profiling
Target architecture
CHANGE
Stakeholder engagement
Steering, working sessions
Kickoff
Weekly working sessions
Core activity
Supporting activity
Hatched: in progress, soft start or tentative
Workshop
Review
Gate
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 65
RESOURCE PLAN
Two roles are short at peak and one is over-resourced
CONTEXT
APPROACH
TEAM
COMMERCIALS
NEXT STEPS
65
ROLE | PEAK DEMAND (FTE) | PLANNED CAPACITY (FTE) | VARIANCE | STATUS
Engagement lead | 0.5 | 0.5 | — | Covered
Product manager | 1 | 1 | — | Covered
Solution architect | 1 | 1 | — | Covered
Data engineer | 1 | 0.5 | −0.5 | Gap
Business analysts | 2 | 2 | — | Covered
Developers | 3 | 2 | −1.0 | Gap
QA lead | 1 | 1 | — | Covered
Change lead | 1 | 1.5 | +0.5 | Over
Net peak position: 1.5 FTE short on developers and data engineering, 0.5 FTE over on change.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 66
RESOURCE PLAN
Each firm role has a named client counterpart
66
Counterparts hold decision rights for their area.
Hours are per week at peak and fall in launch.
A gap in any counterpart slows the matching firm role.
62 hrs
client time per week at peak
7
named counterparts
FIRM ROLE | CLIENT COUNTERPART | HRS PER WEEK
Engagement lead | Executive sponsor | 2
Product manager | Product owner | 20
Solution architect | IT integration lead | 10
Data engineer | Data steward | 6
Business analysts | Patient access SMEs | 8
QA lead | UAT coordinator | 10
Change lead | Department managers | 6
Client commitment | Seven counterparts | 62
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 67
RESOURCE PLAN
The team peaks at 10.8 FTE, then rolls off
67
MOBILIZE
Weeks 1–2: core team and client leads.
DESIGN
Weeks 3–6: BAs and architect at full load.
BUILD AND TEST
Weeks 7–12: developers and QA join.
LAUNCH
Weeks 13–16: ramp-off to support.
LEADERSHIP
DELIVERY
CLIENT
10.8 FTE
peak team size, weeks 7–10
7.9 FTE
average over 16 weeks
4.6 FTE
in week 16, handing over to run
1.2 FTE
client team at peak
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 68
RESOURCE PLAN
A firm team of up to 9.5 FTE delivers in 16 weeks
Source: Sample figures for layout only; replace with current firm data before use.
68
ROLE (FIRM FTE) | MONTH 1 | MONTH 2 | MONTH 3 | MONTH 4
Engagement lead | 0.5 | 0.5 | 0.5 | 0.5
Product manager | 1 | 1 | 1 | 0.5
Solution architect | 1 | 1 | 0.5 | 0.25
Data engineer | 0.5 | 1 | 1 | 0.5
Business analysts (2) | 2 | 2 | 1 | 1
Developers (3) | – | 3 | 3 | 1
QA lead | – | 0.5 | 1 | 1
Change lead | 0.5 | 0.5 | 1 | 1
Total firm FTE | 5.5 | 9.5 | 9 | 5.75
KEY ASSUMPTIONS
Client leads are named by week 1.
Developers start in week 5.
Two-thirds of build is onshore.
PHASE | TEAM RUN RATE / MO
Mobilize | $190K
Design | $310K
Build and test | $460K
Launch | $330K
Peak monthly run rate | $460K
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 69
RESOURCE PLAN
Roles join as work needs them and roll off early
69
WORKSTREAM · ACTIVITY
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
W15
W16
MOBILIZE
DESIGN
BUILD AND TEST
LAUNCH
LEADERSHIP
Engagement lead and PM
1.5 FTE
Solution architect
1.0 FTE
UAT exit
DELIVERY
Data engineer
0.5 to 1.0 FTE
Business analysts
2.0 FTE
Developers
Kickoff
3.0 FTE
QA lead
Design sign-off
0.5 to 1.0 FTE
Full or near full-time
Part-time, ramping
Milestone
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 70
RESOURCE PLAN
Nine named people are in place by February 16
70
MR
Mara R.
Engagement lead
50% · JAN 5 – APR 24
DK
Devon K.
Product manager
100% · JAN 5 – APR 17
SP
Sasha P.
Solution architect
100% TO 25% · JAN 5 – MAR 27
TL
Tariq L.
Data engineer
50% TO 100% · JAN 12 – APR 10
AN
Anya N.
Business analyst
100% · JAN 5 – APR 10
JO
Jonas O.
Business analyst
100% · JAN 5 – APR 10
PC
Priya C.
Lead developer
100% · FEB 2 – APR 24
RB
Rowan B.
QA lead
50% TO 100% · FEB 16 – APR 24
EH
Elena H.
Change lead
50% TO 100% · JAN 19 – APR 24
Allocation is a share of a 40-hour week; ranges show ramp-up or ramp-down.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 71
RESOURCE PLAN
Offshore share grows as the build scales up
Source: Sample figures for layout only; replace with current firm data before use.
71
ONSHORE
NEARSHORE
OFFSHORE
Mobilize
WEEKS 1–2 · 5.5 FTE
Design
WEEKS 3–6 · 8 FTE
Build and test
WEEKS 7–12 · 10.8 FTE
Launch
WEEKS 13–16 · 7.5 FTE
80%
20%
60%
30%
10%
40%
35%
25%
55%
30%
15%
LOCATION | OVERLAP WITH ET
Onshore | 8 hours
Nearshore | 7 to 8 hours
Offshore | 3.5 hours
TIME-ZONE OVERLAP
Offshore overlaps 8:00 to 11:30 ET, so reviews and decisions sit in the morning.
Hand-offs run overnight: offshore builds, onshore reviews next day.
Client ceremonies stay inside the shared window.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 72
RESOURCE PLAN
Loading peaks in weeks 7–8 and eases through launch
72
ROLE | W1–2 | W3–4 | W5–6 | W7–8 | W9–10 | W11–12 | W13–14 | W15–16 | AVG FTE
Engagement lead | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Product manager | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.94
Solution architect | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.25 | 0.25 | 0.69
Data engineer | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.75
Business analysts (2) | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1.5
Developers (3) | – | – | 2 | 3 | 3 | 3 | 2 | 1 | 1.75
QA lead | – | – | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.62
Change lead | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.75
Executive sponsor | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Product owner | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
IT integration lead | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.38
Total FTE | 6.3 | 6.3 | 9.6 | 10.6 | 10.1 | 10.1 | 8.1 | 6.6 | 8.47
LEADERSHIP
DELIVERY
CLIENT
Peak fortnight is weeks 7–8 at 10.6 FTE; client counterparts hold near 1 FTE throughout.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 73
RESOURCE PLAN
Staffing peaks at 10.6 FTE in month 2
73
ROLE | MONTH 1 | MONTH 2 | MONTH 3 | MONTH 4 | AVG FTE
Engagement lead | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Product manager | 1.0 | 1.0 | 1.0 | 0.5 | 0.9
Solution architect | 1.0 | 1.0 | 0.5 | 0.25 | 0.7
Data engineer | 0.5 | 1.0 | 1.0 | 0.5 | 0.8
Business analysts (2) | 2.0 | 2.0 | 1.0 | 1.0 | 1.5
Developers (3) | – | 3.0 | 3.0 | 1.0 | 1.8
QA lead | – | 0.5 | 1.0 | 1.0 | 0.6
Change lead | 0.5 | 0.5 | 1.0 | 1.0 | 0.8
Executive sponsor | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Product owner | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
IT integration lead | 0.25 | 0.5 | 0.5 | 0.25 | 0.4
Total FTE | 6.3 | 10.6 | 10.1 | 6.6 | 8.4
LEADERSHIP
DELIVERY
CLIENT
Peak is month 2: 10.6 FTE, of which the client team provides 1.1.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 74
PRODUCT STRATEGY ROADMAP
Every bet names its assumption and its decision date
Source: Sample figures for layout only; replace with current firm data before use.
74
HORIZON | STRATEGIC BET | ASSUMPTION TO VALIDATE | SIGNAL OF SUCCESS | DECISION POINT
 | Master patient index | Matching rules reach 6% duplicates without manual review at every site. | Duplicates under 8% at two hospitals by Q1 27. | Decide Mar 2027 Buy a matching service if above 9%.
 | Single sign-in | Patients and staff accept one identity without a second login. | 70% of active patients enrolled within 90 days. | Decide Jun 2027 Fall back to staff-assisted enrolment.
 | Self-scheduling | Patients book online when slots are real time and complete. | 30% of primary care visits booked online. | Decide Sep 2027 Pivot to staff-assisted booking if under 20%.
 | Digital intake | Patients finish forms and insurance before they arrive. | 60% complete intake before the visit. | Decide Dec 2027 Cut to insurance capture only if under 40%.
 | Price estimates | Estimates within 10% of the final bill build trust. | Front-end denials under 6%. | Decide Jun 2028 Narrow to scheduled procedures if misses persist.
NOW
NOW
NEXT
NEXT
LATER
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 75
PRODUCT STRATEGY ROADMAP
Three bets carry the vision into a sequenced roadmap
Source: Sample figures for layout only; replace with current firm data before use.
75
PRODUCT VISION
Every Northfield patient reaches, books and pays for care in one digital front door.
1 · Know every patient
OUTCOME
Duplicate records 11% → 6%
One record, one sign-in everywhere.
Now · Master patient index
Next · Single sign-in
Later · Shared patient data store
2 · Open the door
OUTCOME
Visits booked online 8% → 60%
Patients book and arrive ready, no call.
Now · Self-scheduling, primary care
Next · Digital intake
Later · Multilingual booking
3 · Pay and track with confidence
OUTCOME
Front-end denials 9% → 5%
Price and eligibility known up front.
Now · Eligibility checks
Next · Price estimates
Later · Referral tracking
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 76
PRODUCT STRATEGY ROADMAP
Every initiative traces back to the vision
Source: Sample figures for layout only; replace with current firm data before use.
76
PRODUCT VISION
Every Northfield patient reaches, books and pays for care in one digital front door.
NORTH STAR
80% of patients complete access online by 2028.
Baselines are 2026 averages across six hospitals.
OUTCOME | BASELINE → TARGET | INITIATIVES | HORIZON
Duplicate patient records | 11% → 6% | Master patient index | 
Sites on one sign-in | 0 → 6 of 6 | Single sign-in | 
Visits booked online | 8% → 60% | Self-scheduling; digital intake | 
Calls to the access center | 100% → 75% | Waitlist; reminders | 
Front-end denials | 9% → 5% | Eligibility checks; price estimates | 
Referrals completed | 61% → 85% | Referral tracking | 
NOW
NOW
NEXT
NEXT
LATER
LATER
KNOW THE PATIENT
OPEN THE DOOR
PAY AND TRACK
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 77
PRODUCT STRATEGY ROADMAP
Strategy to roadmap: pillars, bets and decision gates
Source: Sample figures for layout only; replace with current firm data before use.
VISION
SEGMENTS
BETS
ROADMAP
MEASURES
77
STRATEGIC PILLAR
Now
Next
Later
OUTCOME · 11% → 6% DUPLICATES
Know every patient
Owner: chief data officer
DECISION · MAR 27
Master patient index
Signal: duplicates under 8%
DECISION · JUN 27
Single sign-in
Signal: 70% enrolled in 90 days
GATE · 2028
Shared data store
Waits for index and sign-in
OUTCOME · 8% → 60% BOOKED ONLINE
Open the door
Owner: patient access officer
DECISION · SEP 27
Self-scheduling
Signal: 30% of visits online
DECISION · DEC 27
Digital intake
Signal: 60% intake before visit
GATE · 2028
Multilingual booking
Booking in every language
OUTCOME · 9% → 5% DENIALS
Pay and track
Owner: VP revenue cycle
GATE · Q2 27
Eligibility checks
Signal: denials under 7%
DECISION · JUN 28
Price estimates
Signal: estimates within 10%
GATE · 2028
Referral tracking
One status view, order to visit
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 78
PRODUCT STRATEGY ROADMAP
One north star, four inputs, the bets that move them
Source: Sample figures for layout only; replace with current firm data before use.
78
North star · patients who complete access online, 24% → 80% by 2028
Identity input
DUPLICATE RECORDS
11% → 6%
BETS THAT MOVE IT
NOW · Q4 26
Master patient index
NEXT · Q1 27
Single sign-in
Booking input
VISITS BOOKED ONLINE
8% → 60%
BETS THAT MOVE IT
NOW · Q1 27
Self-scheduling
LATER · 2028
Multilingual booking
Readiness input
INTAKE DONE BEFORE ARRIVAL
15% → 70%
BETS THAT MOVE IT
NEXT · Q2 27
Digital intake
NEXT · Q3 27
Smart reminders
Price clarity input
FRONT-END DENIALS
9% → 5%
BETS THAT MOVE IT
NEXT · Q2 27
Eligibility checks
LATER · Q3 27
Price estimates
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 79
PRODUCT STRATEGY ROADMAP
Key results by quarter, each tied to its initiative
Source: Sample figures for layout only; replace with current firm data before use.
79
OBJECTIVE | KEY RESULT | INITIATIVE MAPPED | OWNER | CONFIDENCE
Know every patient once | Duplicate records 11% → 9% | Master patient index | Chief data officer | High
 | Sites on one sign-in 0 → 2 of 6 | Single sign-in, pilot sites | Chief digital officer | Medium
Book without a call | Visits booked online 8% → 20% | Self-scheduling, primary care | Chief patient access officer | High
 | Sites on one sign-in 2 → 4 of 6 | Single sign-in, rollout | Chief digital officer | Medium
Arrive ready for the visit | Intake done before arrival 15% → 40% | Digital intake | Director of registration | Medium
 | No-show rate 11% → 9% | Smart reminders | Chief patient access officer | Low
Q4 26
Q1 27
Q2 27
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 80
PRODUCT STRATEGY ROADMAP
Every roadmap item is an outcome with a target
Source: Sample figures for layout only; replace with current firm data before use.
80
Now · Q4 26 to Q1 27
KPI · 11% → 6% DUPLICATE RECORDS
One record per patient
Master patient index
Match rules at six sites
Duplicate review queue
KPI · 0 → 6 OF 6 SITES ON ONE SIGN-IN
One identity everywhere
Single sign-in
Staff identity federation
Patient app login
Next · Q2 to Q3 27
KPI · 8% → 60% VISITS BOOKED ONLINE
Patients book without a call
Self-scheduling, primary care
Digital intake before arrival
Waitlist and cancellations
KPI · 11% → 6% NO-SHOW RATE
Fewer visits lost to forgetting
Smart reminders
Care plans in the app
Reminder channel choice
Later · Q4 27 and 2028
KPI · 9% → 5% FRONT-END DENIALS
Price known before booking
Eligibility checks
Price estimates
Payment plans
KPI · 61% → 85% REFERRALS COMPLETED
Referrals followed to the visit
Referral tracking
Multilingual booking
Caregiver proxy access
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 81
PRODUCT STRATEGY ROADMAP
Strategy on a page: the digital front door to 2028
Source: Sample figures for layout only; replace with current firm data before use.
81
Every Northfield patient reaches, books and pays for care in one digital front door.
TARGET SEGMENTS
Primary care patients booking routine visits
Specialty patients arriving by referral
Caregivers managing care for family
Patients with chronic conditions
PROBLEMS WE SOLVE
No booking without a phone call
Six hospitals, six patient identities
Prices unknown until the bill arrives
Referrals lost between sites
VALUE PROPOSITION
FOR PATIENTS
One sign-in to find, book, prepare for and pay for care, with the price known first.
For staff: one verified record at every site.
STRATEGIC BETS
1.
Know every patient once
2.
Open the door online
3.
Pay and track with confidence
4.
Run on one data foundation
WHAT WE WILL NOT DO
Replace the EHR
Build tools for a single hospital
Add voice or kiosk channels before 2028
Price every service before 2027
SUCCESS MEASURES
80% complete access online by 2028
Calls to the access center down 25%
Front-end denials 9% → 5%
No-show rate 11% → 6%
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 82
PRODUCT STRATEGY ROADMAP
Four themes share capacity across five quarters
Source: Sample figures for layout only; replace with current firm data before use.
82
THEME
CAPACITY
Q4 26 · Now
Q1 27 · Now
Q2 27 · Next
Q3 27 · Next
Q4 27 · Later
Know the patient
25%
Master patient index
Shared data store
Single sign-in
Open the door
40%
Self-scheduling
Digital intake
Pay with confidence
20%
Eligibility checks
Price estimates
Coordinate care
15%
Smart reminders
Referral tracking
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 83
CONTENTS
Six sections and the detail behind each
83
01
Our understanding
Your goals and constraints
The close cycle today
Pain points by entity
What success looks like
02
Approach
Guiding principles
Three-wave plan
Governance and cadence
03
Solution
Target operating model
Systems and automation
Controls and audit readiness
Change and adoption
04
Team
Engagement leadership
Delivery team
Your team's role
05
Commercials
Fees by phase
Assumptions
Business case and payback
06
Why West Monroe
Healthcare finance experience
Comparable client results
References
Our commitment
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 84
CONTENTS
Where to find each part of the proposal
84
01
Our understanding
3
Your goals and constraints
3
The close cycle today
4
Pain points by entity
6
02
Approach
9
Guiding principles
9
Three-wave plan
10
Governance and cadence
12
03
Solution
14
Target operating model
14
Systems and automation
15
Controls and audit readiness
18
04
Team
22
Engagement leadership
22
Delivery team
23
Your team's role
25
05
Commercials
26
Fees by phase
26
Assumptions
27
Business case and payback
28
06
Why West Monroe
30
Healthcare finance experience
30
Comparable client results
31
References
33
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 85
CONTENTS
What sits behind each section
85
Six sections follow. Appendix items A1 to A6 carry the supporting detail.
01
Our understanding
Your goals and constraints · The close cycle today · Pain points by entity · What success looks like
02
Approach
Guiding principles · Three-wave plan · Governance and cadence
03
Solution
Target operating model · Systems and automation · Controls and audit readiness · Change and adoption
04
Team
Engagement leadership · Delivery team · Your team's role
05
Commercials
Fees by phase · Assumptions · Business case and payback
06
Why West Monroe
Healthcare finance experience · Comparable client results · References · Our commitment
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 86
CONTENTS
What each part of the proposal gives you
86
01
Our understanding
What we heard from Northfield leaders about the close, and where time and effort are lost today.
02
Approach
A three-wave plan that fixes the process first, then the systems.
03
Solution
The operating model, tooling and controls that bring the close down to five days.
04
Team
The leaders and specialists who will deliver, and how they work beside your finance team.
05
Commercials
Fees by phase, the assumptions behind them, and a business case that pays back inside 14 months.
06
Why West Monroe
Healthcare finance experience and results from comparable close transformations.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 87
87
CONTENTS
What this proposal covers
Six sections, then supporting detail in the appendix.
01
Our understanding
What we heard from Northfield leaders about the close, and where time and effort are lost today.
02
Approach
A three-wave plan that fixes the process first, then the systems.
03
Solution
The operating model, tooling and controls that bring the close down to five days.
04
Team
The leaders and specialists who will deliver, and how they work beside your finance team.
05
Commercials
Fees by phase, the assumptions behind them, and a business case that pays back inside 14 months.
06
Why West Monroe
Healthcare finance experience and results from comparable close transformations.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.

## Slide 88
CONTENTS
Six sections, from understanding to proof
88
01
Our understanding
What we heard from Northfield leaders about the close, and where time and effort are lost today.
02
Approach
A three-wave plan that fixes the process first, then the systems.
03
Solution
The operating model, tooling and controls that bring the close down to five days.
04
Team
The leaders and specialists who will deliver, and how they work beside your finance team.
05
Commercials
Fees by phase, the assumptions behind them, and a business case that pays back inside 14 months.
06
Why West Monroe
Healthcare finance experience and results from comparable close transformations.
Notes: WMDS bound template. Content classification: synthetic_example. Frozen source and binding provenance are recorded in layout-report.json and binding-report.json.